## ProjectSchedule
Exploring Deep Learning for Real-Time Estimation of Lithium-Ion Battery Capacity: A Proposed Method
Superviosr: Zhong Fan | Start: | 2023-09-25
Student: Zihuan Zhang | Today: | 2024-04-29
| Display Week: | 17 |  |  | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12 | [6 empty] | 2024-02-19 | [6 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [7 empty] | 2024-04-16
 | time axis 2024-01-15 to 2024-04-22
TASK | PROGRESS | START | END | DAYS | time axis 2024-01-15 to 2024-04-22
Project Scope
Scanning Literature | 100% | 2023-09-25 | 2023-10-07 | 13
Comfring topic With Supervisor | 100% | 2023-10-08 | 2023-10-10 | 3
Milestone:Comfriming the research topic | 100% | 2023-10-12 | 2023-10-12 | 1
Preliminary Work
Literature Review | 100% | 2023-10-08 | 2023-11-08 | 32
Choosing Dataset and deep learning method | 100% | 2023-10-08 | 2023-10-20 | 13
Basic Deep Learning Knowledge Learning | 100% | 2023-10-20 | 2023-12-01 | 43
Data Extracting | 100% | 2023-10-20 | 2023-11-20 | 32
Preliminary Report Writing | 100% | 2023-11-20 | 2023-12-08 | 19
Discussing Preliminary Work With Supervisor | 100% | 2023-12-08 | 2023-12-08 | 1
Milestone:Preminary Work Done | 100% | 2023-12-09 | 2023-12-09 | 1
Deep Learning Block Design
Single Block: CNN and BiLSTM | 100% | 2024-01-08 | 2024-01-15 | 8
Block Connecting:CNN-BiLSTM--P-S | 100% | 2024-01-15 | 2024-01-28 | 14
Autoencoder Block Design | 100% | 2024-01-15 | 2024-01-31 | 17
Discussing results With Supervisor | 100% | 2024-02-01 | 2024-02-01 | 1
Milestone:Deep Learning Work Done | 100% | 2024-02-02 | 2024-02-02 | 1
Filter Design
Moving Average Filter Design | 100% | 2024-02-03 | 2024-02-05 | 3
Low Pass Filter Design | 100% | 2024-02-05 | 2024-02-17 | 13
Discussing results with Experts in DSP | 100% | 2024-02-17 | 2024-02-21 | 5
Filter Optimization | 100% | 2024-02-21 | 2024-03-15 | 24
Milestone:Filter Design Completed | 100% | 2024-03-16 | 2024-03-16 | 1
Integration and Test
Final Model Integration | 100% | 2024-03-16 | 2024-03-21 | 6
Integrated Model Result Visualization | 100% | 2024-03-21 | 2024-03-25 | 5
Milestone:Final Model Completed | 100% | 2024-03-26 | 2024-03-26 | 1
Final Report Writing
Draft Report | 100% | 2024-03-26 | 2024-04-04 | 10
Discussing Report with Supervisor | 100% | 2024-04-05 | 2024-04-05 | 1
Report/Model Optimization | 100% | 2024-04-05 | 2024-04-17 | 13
Comfriming with Supervisor | 100% | 2024-04-18 | 2024-04-18 | 1
Milestone:Final Report Completed | 100% | 2024-04-19 | 2024-04-19 | 1
Note on G6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.